**🗓️ PHASE 1 PLAN – 1st June to 15th July (6.5 weeks)**

**🎯 GOAL: Deliver full app experience for Pandit + Yajman + Samagri Store**

**🎁 Outcome: Launch internal beta app + working store + admin dashboard**

| **Week** | **Dates** | **Deliverables** |
| --- | --- | --- |
| **Week 1** | Jun 1 – Jun 7 | 🔧 Tech setup (Flutter + Firebase)🧠 Finalize DB schema + wireframes (yajman, pooja, store)🛠 GitHub repo, CI/CD config |
| **Week 2** | Jun 8 – Jun 14 | 🔐 Pandit Login with OTP🧑 Pandit Profile screen📋 Yajman Add/Edit/View/List/Search |
| **Week 3** | Jun 15 – Jun 21 | 🙏 Pooja Catalog (pre-defined + custom)📋 Material checklist auto-linking to poojas🛒 Samagri Store: UI for product listing & detail view |
| **Week 4** | Jun 22 – Jun 28 | 📆 Pooja Scheduling Calendar (add pooja to date)📲 WhatsApp/Local reminders for pooja bookings🛒 Store: Cart + Checkout UI |
| **Week 5** | Jun 29 – Jul 5 | 🧾 Spiritual Journal: Notes + photo upload after pooja📦 Order tracking: Status flow💳 Payment gateway integration (test mode) |
| **Week 6** | Jul 6 – Jul 12 | 📊 Dashboard (pooja stats, yajman list, earnings)🌐 Yajman Link View (public pooja view)🧪 Testing + Admin Panel for Store Orders |
| **Mid Week** | Jul 13 – Jul 15 | 🐞 Final Fixes📱 Deploy for Beta (APK)🎓 User Onboarding PDF/Video |

**✅ PHASE 1 OUTPUT BY 15 JULY**

| **Module** | **Features** |
| --- | --- |
| Pandit App | Login, Profile, Yajman CRUD, Pooja Catalog |
| Pooja Scheduling | Calendar Booking, Checklist, Notifications |
| Journal | Notes, Photo Upload |
| Samagri Store | Products, Cart, Checkout, Payment (Test Mode), Order Tracking |
| Admin Panel | Order View, Manual Status Update |
| Yajman Portal | Public Pooja Summary Link |
| Reports | Total Poojas, Yajman Count, Popular Poojas |
| Deployments | APK (Play Store Internal), Admin Dashboard Access |

**🧘‍♂️ PHASE 2: Online Pooja + Add-on Features**

**Start:** 16th July
**Duration:** ~6 weeks (till 31st August)

| **Week** | **Dates** | **Deliverables** |
| --- | --- | --- |
| **Week 7** | Jul 16 – Jul 22 | 🎥 Online Pooja UI: Schedule + Select Platform (Jitsi/Zoom) |
| **Week 8** | Jul 23 – Jul 29 | 🔗 Integration with Jitsi/Zoom APIs📲 Auto-generate & send link via WhatsApp |
| **Week 9** | Jul 30 – Aug 5 | 🎥 Test pooja session with reminders💬 Feedback capture post session |
| **Week 10** | Aug 6 – Aug 12 | 🔁 Add Recurring Pooja Booking🔒 Login for Yajmans (optional) |
| **Week 11** | Aug 13 – Aug 19 | 💳 Payment Gateway for Online Pooja (per session)📋 E-certificate or Sankalp PDF after session |
| **Week 12** | Aug 20 – Aug 31 | 🧪 Final Testing🎉 Public Launch for Online Pooja & Store📲 Play Store Production Submission |

**🔮 Suggested Add-on Features in Phase 2**

* 🌐 Multi-language support (Hindi/English)
* 📅 Recurring pooja schedule (e.g. every Monday)
* 📥 Downloadable PDF (Sankalp, pooja result)
* 🧑‍🤝‍🧑 Yajman feedback & rating system
* 🧘 Guided Meditation / Mantra Audio
* 🔄 Sync Google Calendar for reminders